## APPENDIX B
CLC PRODUCTIVITY RISK FACTOR ESTIMATE
APPENDIX B
| COST HEADING | PRE-COVID ESTIMATE |  | COVID PRODUCTIVITY FACTOR CALCULATIONS |  | POST COVID ESTIMATE | % UPLIFT (COVID-19 PRODUCTIVITY RISK FACTOR)
1 | MEASURED WORK
1.1 | Labour | 45% | 4500000 | Productivity Factor (Post/Pre) | 95% | 4725000 | 1.672%
|  |  |  | Productivity Loss | 5%
|  |  |  | Applied Factor | 105%
|  |  |  | Proportion of measured work affected | 100%
|  |  |  | Total Applied Factor | 105%
1.2 | Plant | 5% | 500000 | Productivity Factor (Post/Pre) | 100% | 500000 | 0%
|  |  |  | Productivity Loss | 0%
|  |  |  | Applied Factor | 100%
|  |  |  | Proportion of Measured work affected | 100%
|  |  |  | Total Applied Factor | 100%
1.3 | Material | 50% | 5000000 | No adjustments |  | 5000000 | 0%
| MEASURED WORK TOTAL | 100% | 10000000 |  |  | 10225000 | 1.672%
2 | PRELIMINARIES
2.1 | Total Preliminaries | 13% | 1300000 | Additional prelims |  | 1638000 | 2.512%
|  |  |  | Prelims Factor | 105%
|  |  |  | Total Including additional | 1365000
Prolongation
|  |  |  | Pre-covid duration | 52
|  |  |  | Weekly rate (including thickening) | 26250
|  |  |  | Covid related productivity attained | 75%
|  |  |  | Productivity Loss (time) | 25%
|  |  |  | Mitigation Estimate | 5%
|  |  |  | Applied Factor | 20%
|  |  |  | Adjusted programme | 62.4
| Sub-total |  | 11300000 |  |  | 11863000 | 4.184%
3 | OVERHEADS & PROFIT | 7% | 791000 | No adjustments | 7% | 830410 | 0.2929%
4 | RISK | 5% | 604550 | Original Factor | 5% | 761604.6 | 1.167%
|  |  |  | Additional Covid Productivity Risk | 1%
|  |  |  | Total Post Covid | 6%
5 | TOTAL |  | 12695550 |  |  | 13455014.6 | 5.644%
TOTAL COVID-19 PRODUCTIVITY FACTOR TO BE APPLIED p
+ MARKET CONDITIONS FACTOR = TOTAL ADJUSTMENT TO ESTIMATE
User input cells
User input cells using the CLC toolkit measures on productivity assessment